## Backlog
Riviso — Production Hardening & Scale Tracker (Target ~50 users)
Phase | ID | Category | Item | Severity / Priority | Effort | Evidence (file:line) | Fix / Action | Verification | Status | Owner | Notes
PHASE 0 — Critical Security (stop-the-bleed)
P0 | S0.1 | Security | Fail-fast on placeholder/short SECRET_KEY in production | Critical | S | core/config.py:47-49; core/production.py:67-71 | Raise at startup if ENVIRONMENT=production and key is default or <32 chars | Boot with bad key exits non-zero | Not Started
P0 | S0.2 | Security | Remove hardcoded admin seed 'Admin@2026' | Critical | S | app.py:52-78 | Delete seed; env-gated one-time bootstrap CLI | grep finds no literal password; fresh DB has no default admin | Not Started
P0 | S0.3 | Security | Stop returning WordPress app password in API responses | High | S | routes/wordpress.py:537,584-585; schemas/project_settings.py:34-36 | Return wp_app_password_set: bool only | Response JSON contains no secret | Not Started
P0 | S0.4 | Security | Disallow MONGODB_TLS_INSECURE & OAUTHLIB_INSECURE_TRANSPORT in prod | High | S | database.py:88-93; app.py:33-36 | Startup check rejects insecure transport in production | Prod boot fails if flags set | Not Started
P0 | S0.5 | Security | Confirm legacy Flask app.py is not deployed/reachable | High | M | app.py (whole) | Remove from deploy target or gate behind disabled flag | No prod route served by Flask | Not Started
PHASE 1 — Security Hardening
P1 | S1.1 | Security | Refresh-token rotation + server-side invalidation | High | M | routes/auth.py:700-790 | Issue new RT each refresh; track jti allow/deny list | Reused old RT is rejected | Not Started
P1 | S1.2 | Security | Rate-limit /auth/refresh | High | S | routes/auth.py:700 | @limiter.limit('20/minute') | 429 after threshold | Not Started
P1 | S1.3 | Security | Move JWT tokens out of localStorage to httpOnly cookies | High | M | frontend/src/lib/api.ts:1038-1060,1282-1347 | Cookie-only auth; remove localStorage | No tokens in localStorage; XSS cannot read | Not Started
P1 | S1.4 | Security | Cookie Secure default true in prod + max_age aligned to TTL | Medium | S | core/config.py:53; routes/auth.py:127-163,772-788 | Secure+SameSite+expiry | Cookies have Secure+expiry in prod | Not Started
P1 | S1.5 | Security | Account lockout after N failed logins | Medium | M | routes/auth.py:187 | Per-email backoff/lockout | Lockout triggers in test | Not Started
P1 | S1.6a | Security | SSRF guard on WordPress URL fetch (block private/metadata IPs) | High | M | routes/wordpress.py:140-146; services/wordpress_client.py:45-81 | URL allowlist + IP guard; restrict redirects | Request to 169.254.169.254 / 10.x blocked | Not Started
P1 | S1.6b | Security | SSRF guard on Shopify shop resolution | High | M | services/shopify_oauth.py:132-137 | Require *.myshopify.com / Admin API only | Non-shopify host rejected | Not Started
P1 | S1.6c | Security | SSRF guard on featured-image + OpenAI ref-image download | High | M | services/wordpress_client.py:231-237; services/shopify_article_image.py:47-61; services/openai_client.py:175-178 | HTTPS host allowlist / data-URL only | Internal IP fetch blocked | Not Started
P1 | S1.7 | Security | CSRF protection for cookie auth | Medium | M | core/deps.py:38-46 | Require X-Requested-With on mutations or SameSite=Strict | Cross-site POST without header rejected | Not Started
P1 | S1.8 | Security | Drop localhost origins from production CORS | Medium | S | main.py:72-87,234-240 | Env-only strict allowlist in production | Prod CORS excludes localhost | Not Started
P1 | S1.9 | Security | Rate-limit expensive endpoints (generate/bulk-upload/publish/research) | Medium | M | core/ratelimit.py:13 | Per-user limits on OpenAI-backed routes | 429 after threshold per user | Not Started
P1 | S1.10 | Security | Trust-proxy config so rate-limit key is not XFF-spoofable | Medium | S | core/ratelimit.py:11-13 | Configure trusted proxy or key by user id | Spoofed XFF does not bypass limit | Not Started
P1 | S1.11 | Security | Split public liveness from detailed readiness /health | Medium | S | routes/health.py:49-60 | Public {status:ok}; detail behind auth | Anon /health leaks no internals | Not Started
P1 | S1.12 | Security | Close plan bypasses: humanize + export-consume | Medium | M | routes/articles.py:1723; routes/articles.py:901-936 | Add require_plan_action; server-side export gating | Over-quota humanize/export blocked | Not Started
P1 | S1.13 | Security | Authenticate WordPress plugin ZIP download | Medium | S | routes/wordpress.py:508-527 | Require auth or signed token | Anon download returns 401 | Not Started
P1 | S1.14 | Security | Add Next.js security headers | Low | S | frontend/next.config.ts:15-27 | headers() with HSTS/CSP/X-Frame | Headers present on frontend responses | Not Started
PHASE 2 — Performance Quick Wins
P2 | P2.1 | Performance | Request-scoped cache for user/subscription/plan | High | M | core/deps.py:58-60; middleware/plan_limits.py:79-90; services/plan_gatekeeper.py:92-97 | Attach to request.state; gatekeeper reads it | 1 user read per request (not 3-5) | Not Started
P2 | P2.2 | Performance | TTL cache for load_plans() | Medium | S | storage.py:1205; services/plan_gatekeeper.py:49-58 | Module cache ~60s invalidated on upsert_plan | Plans read once per TTL window | Not Started
P2 | P2.3 | Performance | Wrap all sync storage in run_sync on hot async paths | High | M | core/deps.py:58-60; core/project_lookup.py:27-45; routes/wordpress.py:470 | await run_sync(...) everywhere | No sync PyMongo on event loop (profiler) | Not Started
P2 | P2.4 | Performance | Add load_articles_by_ids_for_project; drop 20k scans | High | M | routes/articles.py:1028-1037; routes/scheduled_jobs.py:246-256 | $in query batch fetch | Bulk validate uses single $in query | Not Started
P2 | P2.5 | Performance | asyncio.gather serial pairs (editor-shell, board, shopify sync) | Medium | M | routes/articles.py:1248-1262; routes/scheduled_jobs.py:284-295; services/shopify_sync.py:196-250 | Concurrent independent awaits | Latency = max not sum | Not Started
P2 | P2.6 | Frontend | Visibility guard + backoff on all poll loops | Medium | M | frontend/src/lib/api.ts:788-844; app/projects/[projectId]/page.tsx:1763-1774,3096-3120 | document.hidden check + backoff | No polling when tab hidden | Not Started
P2 | P2.7 | Frontend | Replace listArticlesAll waterfall with aggregate endpoint | High | M | frontend/src/lib/api.ts:1963-1975; page.tsx:1283-1322 | Use workspaceOverview() | Overview loads 1 request not 50 | Not Started
P2 | P2.8 | Frontend | Stop shell refetch on tab switch; dedupe GSC analytics | Medium | S | page.tsx:1171-1218,1290-1372,2508-2521 | Drop tab from deps; share analytics in state | Tab switch fires no shell refetch | Not Started
PHASE 3 — Infrastructure for ~50 Users
P3 | I3.1 | Infrastructure | Separate worker & scheduler from API processes | High | M | main.py:129-138 (lifespan); Procfile | API ENABLE_SCHEDULER=0/worker=0 + 1 worker + 1 scheduler proc | API process runs no scheduler/worker | Not Started
P3 | I3.2 | Infrastructure | Managed MongoDB Atlas M10 (TLS, IP allowlist, backups) | High | M | database.py:88-93 | Atlas M10, TLS on, maxIdleTimeMS=30000 | App connects to M10 over TLS | Not Started
P3 | I3.3 | Infrastructure | Managed Redis (auth + TLS) | High | S | services/generation_queue.py | Single managed Redis with auth/TLS | Queue uses managed Redis | Not Started
P3 | I3.4 | Infrastructure | Automated daily backups + tested restore | High | S | Atlas / ops | Continuous backup; quarterly restore drill | Restore drill succeeds | Not Started
P3 | I3.5 | Infrastructure | TLS termination + HSTS + gzip at Nginx/Cloudflare | High | S | nginx/ | Force HTTPS redirect + HSTS | HTTP redirects to HTTPS; HSTS header set | Not Started
P3 | I3.6 | Infrastructure | Connection pool sizing across processes | Medium | S | database.py | Set maxPoolSize per process; sum < Atlas limit | No connection-limit errors under load | Not Started
P3 | I3.7 | Infrastructure | Healthchecks + auto-restart (liveness/readiness) | Medium | S | routes/health.py | Container healthcheck -> restart policy | Killed proc auto-restarts | Not Started
P3 | I3.8 | Infrastructure | 2-instance API behind LB + rolling deploy | Medium | M | deploy/ | 2 small API instances; zero-downtime deploy | Deploy with no downtime | Not Started
P3 | I3.9 | Infrastructure | Secrets via env/secret manager (not files) | Medium | S | .env files | Move to host secret store | No secrets on disk in prod | Not Started
P3 | I3.10 | Infrastructure | Rate-limit store in Redis (not in-memory) | Medium | S | core/ratelimit.py | SlowAPI -> Redis storage backend | Limits consistent across 2 instances | Not Started
P3 | I3.11 | Infrastructure | Email reliability: queue or native SMTP lib | Medium | M | services/email_dispatch.py | Replace Node subprocess or queue jobs | Email send retried on failure | Not Started
PHASE 4 — Structural Refactor (data / OOP layer)
P4 | P4.1 | Performance | Add Mongo projections (project/user/scheduler light vs full) | High | M | storage.py:2323,2490,1515,3683 | Per-call-site projections | Hot reads exclude heavy fields | Not Started
P4 | P4.2 | Performance | Route partial writes through $set; batch bulk_update_articles | High | M | storage.py:4104-4113,4167-4177 | bulk_write of $set ops | No full-doc replace on field update | Not Started
P4 | P4.3 | Performance | Persist has_body + derived listing status | High | M | storage.py:3045-3060; routes/articles.py:731-795 | Write-time flags + $match | Listing avoids body scan | Not Started
P4 | P4.4 | Performance | Bulk scheduled-job APIs; move heal to worker | Medium | M | routes/scheduled_jobs.py:38-78,717-771 | delete_many; background heal | GET board does no writes | Not Started
P4 | P4.5 | Performance | Add missing indexes/TTLs (site_maps, monitors, research_cache) | Medium | S | database.py:191-229 | create_index + TTL | explain() shows index use | Not Started
P4 | P4.6 | Architecture | Typed repositories + domain models (heavy/light fields) | High | L | storage.py (whole) | ArticleRepository/ProjectRepository/etc. | Business code uses typed models | Not Started
P4 | P4.7 | Architecture | RequestContext carrying memoized user/project/plan | Medium | M | core/deps.py | DI object | Single fetch per request entity | Not Started
P4 | P4.8 | Performance | Expand Motor async coverage for hot reads | Medium | L | services/mongo_listings_async.py | Async reads off thread pool | Thread pool not saturated under load | Not Started
PHASE 5 — Observability, Testing & CI
P5 | I5.1 | Observability | Error tracking (Sentry) API+worker+frontend with PII scrub | High | S | — | Integrate Sentry SDKs | Test exception appears in Sentry | Not Started
P5 | I5.2 | Observability | Metrics + dashboards (latency, queue depth, Mongo op time) | Medium | M | — | Prometheus/Grafana or hosted | Dashboards live | Not Started
P5 | I5.3 | Observability | Structured logging with request IDs | Medium | S | core/logging.py | Correlation IDs across API/worker | Logs correlate by request id | Not Started
P5 | I5.4 | CI/CD | CI: pip-audit/Dependabot + secret scanning (gitleaks) | High | S | .github/workflows | Block merges on Critical | PR fails on planted secret | Not Started
P5 | I5.5 | CI/CD | CI: backend pytest + frontend unit tests on PR | High | S | backend/tests; frontend | Green gate to deploy | PR blocked on test failure | Not Started
P5 | I5.6 | Testing | Integration tests for auth, plan gating, publish flows | High | M | backend/tests | Cover security-sensitive paths | Critical flows covered | Not Started
P5 | I5.7 | Observability | Uptime monitoring + alerting on /health readiness | Medium | S | routes/health.py | External monitor + alerts | Downtime pages on-call | Not Started
PHASE 6 — Launch Readiness
P6 | L6.1 | Launch | Load test @ 15 concurrent users / realistic mix | High | M | — | k6/Locust scenario | p95 within target, no errors | Not Started
P6 | L6.2 | Launch | Security re-scan (verify P0/P1 closed) | High | S | — | Re-run audit | No High/Critical open | Not Started
P6 | L6.3 | Launch | Runbook + on-call + incident process | Medium | S | docs | Document runbook | Runbook reviewed | Not Started
P6 | L6.4 | Launch | Disaster recovery drill (restore from backup) | High | S | Atlas | Restore drill | RTO/RPO verified | Not Started
P6 | L6.5 | Launch | Data retention & privacy review (account deletion purges data) | Medium | M | routes/profile.py | Verify deletion end-to-end | Deleted account leaves no data | Not Started

## Dashboard
Progress Dashboard
By Status | Count
Not Started
In Progress
Blocked
In Review
Done
Deferred
TOTAL TASKS
% Complete
By Phase | Total | Done
PHASE 0 — Critical Security (stop-the-bleed)
PHASE 1 — Security Hardening
PHASE 2 — Performance Quick Wins
PHASE 3 — Infrastructure for ~50 Users
PHASE 4 — Structural Refactor (data / OOP layer)
PHASE 5 — Observability, Testing & CI
PHASE 6 — Launch Readiness

## Legend
Legend & Conventions
Severity
Critical | Exploitable now / secrets exposed — fix before anything else
High | Serious risk or large perf/scale impact — Phase 0/1/2
Medium | Important, bounded impact — schedule within phase
Low | Cleanup / future-proofing
Effort
S | Small — < 1 day
M | Medium — 1-3 days
L | Large — 1 week+
Status values | Not Started, In Progress, Blocked, In Review, Done, Deferred
ID prefix S | Security item (see RIVISO_PRODUCTION_HARDENING_PLAN.md §A)
ID prefix P2/P4 | Performance item (see RIVISO_PERFORMANCE_OPTIMIZATION_AUDIT.md)
ID prefix I | Infrastructure / Ops item
ID prefix L | Launch readiness item
Evidence | Backend paths are relative to backend/app unless app.py/storage.py/database.py (repo root)